## 基建工程量表 --模板
请认真阅读使用说明表。 | [9 empty] | 2.5 | 0.004 | 0.02 | 0.5 | [606 empty] | 三心拱巷道 |  | 圆形巷道 |  | 矩形巷道 |  |  | 梯形巷道
序号 | 工程名称 | 支护（mm） |  | 断面 |  | 长度 | 开掘量 | 支护砼量 | 铺底碎石 | 锚杆+托盘 | 网片 | 钢筋 | 钢材 | 备注 | 施工定额 | 开始时间 | 结束时间 | 完成时间 | 第一年 | [119 empty] | 第二年 | [119 empty] | 第三年 | [119 empty] | 第四年 | [119 empty] | 第五年 | [119 empty] | 铺底厚 | 净宽 | 净高 | 净直径 | 掘直径 | 净宽 | 净高 | 掘面积 | 净顶 | 净底 | 净高 | 掘面积
|  | 形式 | 厚度 | 净(m2) | 掘(m2) | (m) | (m³) | (m³) | （m³） | （套） | （t） | （t） | （t） |  | m/月或m³/月 |  |  | 月 | 1 | [9 empty] | 2 | [9 empty] | 3 | [9 empty] | 4 | [9 empty] | 5 | [9 empty] | 6 | [9 empty] | 7 | [9 empty] | 8 | [9 empty] | 9 | [9 empty] | 10 | [9 empty] | 11 | [9 empty] | 12 | [9 empty] | 1 | [9 empty] | 2 | [9 empty] | 3 | [9 empty] | 4 | [9 empty] | 5 | [9 empty] | 6 | [9 empty] | 7 | [9 empty] | 8 | [9 empty] | 9 | [9 empty] | 10 | [9 empty] | 11 | [9 empty] | 12 | [9 empty] | 1 | [9 empty] | 2 | [9 empty] | 3 | [9 empty] | 4 | [9 empty] | 5 | [9 empty] | 6 | [9 empty] | 7 | [9 empty] | 8 | [9 empty] | 9 | [9 empty] | 10 | [9 empty] | 11 | [9 empty] | 12 | [9 empty] | 1 | [9 empty] | 2 | [9 empty] | 3 | [9 empty] | 4 | [9 empty] | 5 | [9 empty] | 6 | [9 empty] | 7 | [9 empty] | 8 | [9 empty] | 9 | [9 empty] | 10 | [9 empty] | 11 | [9 empty] | 12 | [9 empty] | 1 | [9 empty] | 2 | [9 empty] | 3 | [9 empty] | 4 | [9 empty] | 5 | [9 empty] | 6 | [9 empty] | 7 | [9 empty] | 8 | [9 empty] | 9 | [9 empty] | 10 | [9 empty] | 11 | [9 empty] | 12 | [9 empty] | （m） | （m） | （m） | （m） | （m） | （m） | （m） | （m） | （m） | （m） | （m） | （m）
一 | 准备时间 | [14 empty] | 1 | 10 | 1 | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [590 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
二 | 二采区 | [6 empty] | 0 | [9 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
1 | 660m斜坡道（660～410m） | [6 empty] | 0 | [9 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
1.1 | 斜坡道口段 | 钢筋，砼 | 300 | 22.24 | 27.76 | 10 | 277.6 | 55 |  |  |  | 3 |  | 5.0m×4.8m，C25 | 80 | 11 | 12 | 0.1 | [10 empty] | ━ | ━ | [588 empty] | 铺底厚: 0.3; 三心拱巷道 净宽: 5; 三心拱巷道 净高: 4.8; 圆形巷道 净直径: 0; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
1.2 | 基岩段 | 喷砼 | 100 | 22.24 | 25.05 | 1657 | 41507.85 | 4656 | [5 empty] | 5.0m×4.8m | 80 | 13 | 220 | 20.7 | [12 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [380 empty] | 铺底厚: 0.3; 三心拱巷道 净宽: 5; 三心拱巷道 净高: 4.8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
1.3 | 错车道 | 喷砼 | 100 | 22.24 | 25.05 | 200 | 5010 | 562 | [5 empty] | 5.0m×4.8m，8个 | 80 | 221 | 246 | 2.5 | [220 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [354 empty] | 铺底厚: 0.3; 三心拱巷道 净宽: 5; 三心拱巷道 净高: 4.8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
1.4 | 躲避硐室 | 喷砼 | 100 | 1.93 | 2.41 | 180 | 433.8 | 86 | [5 empty] | 1.0m×2.0m，90个 |  |  | 0 | 0 | [600 empty] | 铺底厚: 0; 三心拱巷道 净宽: 1; 三心拱巷道 净高: 2; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 2047 | 47229.25 | 5359 | 0 | 0 | 0 | 3 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
2 | 2#副井（660～195m） | [6 empty] | 0 | [8 empty] | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
2.1 | 井筒段 | 砼 | 300 | 19.63 | 24.62 | 465 | 11448.3 | 2320 |  |  |  |  | 232.5 | φ5.0m | 80 | 11 | 69 | 5.8 | [10 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [531 empty] | 圆形巷道 净直径: 5; 圆形巷道 掘直径: 5.6; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0 | 0.1656
2.2 | 马头门 | 喷砼 | 100 | 13.41 | 16.59 | 20 | 331.8 | 64 | [5 empty] | 共2个 |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 485 | 11780.1 | 2384 | 0 | 0 | 0 | 0 | 232.5 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
3 | 北回风井（720~410m） | [6 empty] | 0 | [8 empty] | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
3.1 | 井筒段 | 砼 | 100 | 9.62 | 10.75 | 310 | 3332.5 | 350 | [5 empty] | φ3.5m | 80 | 11 | 50 | 3.9 | [10 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [550 empty] | 圆形巷道 净直径: 3.5; 圆形巷道 掘直径: 3.7; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
3.2 | 马头门 | 喷砼 | 100 | 13.41 | 16.59 | 10 | 165.9 | 32 | [5 empty] | 共1个 |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 320 | 3498.4 | 382 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
4 | 南回风井（800~495） | [6 empty] | 0 | [8 empty] | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
4.1 | 井筒段 | 砼 | 300 | 12.56 | 16.61 | 265 | 4401.65 | 1073 |  |  |  |  | 26.5 | φ4.0m | 80 | 11 | 44 | 3.3 | [10 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [556 empty] | 圆形巷道 净直径: 4; 圆形巷道 掘直径: 4.6; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
4.2 | 马头门 | 喷砼 | 100 | 13.41 | 16.59 | 20 | 331.8 | 64 | [5 empty] | 共1个 |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 285 | 4733.45 | 1137 | 0 | 0 | 0 | 0 | 26.5 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
5 | 矿石溜井 | [6 empty] | 0 | [9 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
5.1 | 北溜井（410~210） |  |  | 9.62 | 9.62 | 200 | 1924 | 0 | [5 empty] | φ3.5m | 80 | 215 | 240 | 2.5 | [214 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [360 empty] | 圆形巷道 净直径: 3.5; 圆形巷道 掘直径: 3.5; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
5.2 | 南溜井（450~210） |  |  | 9.62 | 9.62 | 240 | 2308.8 | 0 | [5 empty] | φ3.5m | 80 | 258 | 288 | 3 | [257 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [312 empty] | 圆形巷道 净直径: 3.5; 圆形巷道 掘直径: 3.5; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
5.3 | 集中溜井（210~10）1 |  |  | 9.62 | 9.62 | 400 | 3848 | 0 | [5 empty] | φ3.5m，2条 | 80 | 323 | 373 | 5 | [322 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [227 empty] | 圆形巷道 净直径: 3.5; 圆形巷道 掘直径: 3.5; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 840 | 8080.8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
6 | V主井 | [6 empty] | 0 | [9 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
6.1 | V主井延深（-30~-120） | 砼 | 300 | 15.9 | 20.42 | 90 | 1837.8 | 407 |  |  |  |  | 45 | φ4.5m | 80 | 11 | 22 | 1.1 | [10 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [578 empty] | 圆形巷道 净直径: 4.5; 圆形巷道 掘直径: 5.1; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
6.2 | 溜破系统 |  |  |  |  | 40 | 2600 | 520 | [6 empty] | 800 | 234 | 267 | 3.3 | [233 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [333 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
6.3 | 装矿系统 | 喷砼 | 100 | 16.58 | 17.69 | 50 | 2575 | 56 | [6 empty] | 800 | 201 | 233 | 3.2 | [200 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [367 empty] | 三心拱巷道 净宽: 4.5; 三心拱巷道 净高: 4; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
6.4 | 粉矿回收+联络道 | 喷砼 | 100 | 16.58 | 17.69 | 1419 | 25102.11 | 1575 | [5 empty] | 4.5m×4.0m | 80 | 23 | 200 | 17.7 | [22 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [400 empty] | 三心拱巷道 净宽: 4.5; 三心拱巷道 净高: 4; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 1599 | 32114.91 | 2558 | 0 | 0 | 0 | 0 | 45 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
7 | Ⅷ矿带辅助斜坡道 | [15 empty] | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
7 | 斜坡道段 | 喷砼 | 100 | 20.46 | 21.71 | 295 | 6404.45 | 369 | [5 empty] | 4.8m×4.6m | 80 | 70 | 107 | 3.7 | [69 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [493 empty] | 三心拱巷道 净宽: 4.8; 三心拱巷道 净高: 4.6; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
7.2 | 躲避硐室 | 喷砼 | 100 | 1.93 | 2.41 | 10 | 24.1 | 5 | [5 empty] | 1.0m×2.0m，5个 |  |  | 0 | 0 | [600 empty] | 三心拱巷道 净宽: 1; 三心拱巷道 净高: 2; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 305 | 6428.55 | 374 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
8 | Ⅷ矿带进风井（410~370） | [6 empty] | 0 | [8 empty] | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
8 | Ⅷ矿带进风井（410~370） | 喷砼 | 100 | 9.62 | 10.75 | 40 | 430 | 45 | [5 empty] | φ3.5m | 80 | 70 | 75 | 0.5 | [69 empty] | ━ | ━ | ━ | ━ | ━ | ━ | [525 empty] | 圆形巷道 净直径: 3.5; 圆形巷道 掘直径: 3.7; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 40 | 430 | 45 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
9 | V矿带通风管缆井（210~10） | [6 empty] | 0 | [8 empty] | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
9.1 | 井筒段 | 喷砼 | 100 | 7.07 | 8.04 | 200 | 1608 | 194 |  |  |  |  | 20 | φ3.0m | 80 | 323 | 348 | 2.5 | [322 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [252 empty] | 圆形巷道 净直径: 3; 圆形巷道 掘直径: 3.2; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 200 | 1608 | 194 | 0 | 0 | 0 | 0 | 20 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
10 | 集中运输中段 | [16 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
10.1 | 210m集中运输中段 | 喷砼 | 100 | 7.06 | 7.84 | 2860 | 22422.4 | 2231 | [5 empty] | 2.5m×3.0m | 120 | 70 | 308 | 23.8 | [69 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [292 empty] | 铺底厚: 0; 三心拱巷道 净宽: 2.5; 三心拱巷道 净高: 3; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
10.2 | 210m集中运输中段错车道 | 喷砼 | 100 | 16.58 | 17.69 | 150 | 2653.5 | 167 | [5 empty] | 4.5m×4.0m | 120 | 309 | 322 | 1.3 | [308 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [278 empty] | 铺底厚: 0; 三心拱巷道 净宽: 4.5; 三心拱巷道 净高: 4; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
10.3 | 60m集中运输中段1 | 喷砼 | 100 | 7.06 | 7.84 | 2930 | 22971.2 | 2285 | [5 empty] | 2.5m×3.0m | 120 | 51 | 295 | 24.4 | [50 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [305 empty] | 铺底厚: 0; 三心拱巷道 净宽: 2.5; 三心拱巷道 净高: 3; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
10.4 | 60m集中运输中段2 | 喷砼 | 100 | 7.06 | 7.84 | 1299 | 10184.16 | 1013 | [5 empty] | 2.5m×3.0m | 120 | 201 | 309 | 10.8 | [200 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [291 empty] | 铺底厚: 0; 三心拱巷道 净宽: 2.5; 三心拱巷道 净高: 3; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
10.5 | 60m集中运输中段错车道 | 喷砼 | 100 | 16.58 | 17.69 | 200 | 3538 | 222 | [5 empty] | 4.5m×4.0m | 120 | 310 | 327 | 1.7 | [309 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [273 empty] | 铺底厚: 0; 三心拱巷道 净宽: 4.5; 三心拱巷道 净高: 4; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 7439 | 61769.26 | 5918 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11 | 基建生产中段 | [16 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.1 | 495m回风中段1 | 喷砼 | 100 | 22.24 | 23.55 | 2280 | 53694 | 2987 | [5 empty] | 5.0m×4.8m | 120 | 11 | 201 | 19 | [10 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [399 empty] | 三心拱巷道 净宽: 5; 三心拱巷道 净高: 4.8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.2 | 495m回风中段2 | 喷砼 | 100 | 22.24 | 23.55 | 1654 | 38951.7 | 2167 | [5 empty] | 5.0m×4.8m | 120 | 45 | 183 | 13.8 | [44 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [417 empty] | 三心拱巷道 净宽: 5; 三心拱巷道 净高: 4.8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.3 | 450m生产中段1 | 喷砼 | 100 | 20.46 | 21.71 | 3740 | 81195.4 | 4675 | [5 empty] | 4.8m×4.6m | 120 | #REF! | #REF! | 31.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 三心拱巷道 净宽: 4.8; 三心拱巷道 净高: 4.6; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.4 | 450m生产中段2 | 喷砼 | 100 | 20.46 | 21.71 | 877 | 19039.67 | 1096 | [5 empty] | 4.8m×4.6m | 120 | 184 | 257 | 7.3 | [183 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [343 empty] | 三心拱巷道 净宽: 4.8; 三心拱巷道 净高: 4.6; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.5 | 450m回风上山 | 锚网 |  | 9.26 | 9.26 | 550 | 5093 | 0 | [5 empty] | 4.2m×2.5m | 120 | 202 | 248 | 4.6 | [201 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [352 empty] | 三心拱巷道 净宽: 4.2; 三心拱巷道 净高: 2.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.6 | 410m回风中段1 | 喷砼 | 100 | 22.24 | 23.55 | 2430 | 57226.5 | 3183 | [5 empty] | 5.0m×4.8m | 120 | 11 | 214 | 20.3 | [10 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [386 empty] | 三心拱巷道 净宽: 5; 三心拱巷道 净高: 4.8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.7 | 410m回风中段2 | 喷砼 | 100 | 22.24 | 23.55 | 1950 | 45922.5 | 2555 | [5 empty] | 5.0m×4.8m | 120 | 51 | 214 | 16.3 | [50 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [386 empty] | 三心拱巷道 净宽: 5; 三心拱巷道 净高: 4.8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.8 | 370m生产中段1 | 喷砼 | 100 | 20.46 | 21.71 | 980 | 21275.8 | 1225 | [5 empty] | 4.8m×4.6m | 120 | 76 | 158 | 8.2 | [75 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [442 empty] | 三心拱巷道 净宽: 4.8; 三心拱巷道 净高: 4.6; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.9 | 370m生产中段2 | 喷砼 | 100 | 20.46 | 21.71 | 1117 | 24250.07 | 1396 | [5 empty] | 4.8m×4.6m | 120 | 215 | 308 | 9.3 | [214 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [292 empty] | 三心拱巷道 净宽: 4.8; 三心拱巷道 净高: 4.6; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
11.10 | 370m回风上山 | 锚网 |  | 9.26 | 9.26 | 317 | 2935.42 | 0 | [5 empty] | 4.2m×2.5m | 120 | 309 | 335 | 2.6 | [308 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [265 empty] | 三心拱巷道 净宽: 4.2; 三心拱巷道 净高: 2.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 15895 | 349584.06 | 19284 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12 | 硐室工程 | [16 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.1 | 中央变电所 | 锚网喷砼 | 100 | 14.33 | 15.34 | 27 | 414.18 | 27 |  | 73 | 0.432 |  |  | 4.5m×3.5m | 800 | 215 | 220 | 0.5 | [214 empty] | ━ | ━ | ━ | ━ | ━ | ━ | [380 empty] | 三心拱巷道 净宽: 4.5; 三心拱巷道 净高: 3.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.2 | 中央变电所联巷 |  |  | 14.87 | 14.87 | 40 | 594.8 | 0 | [5 empty] | 4.0m×4.0m | 120 | 221 | 224 | 0.3 | [220 empty] | ━ | ━ | ━ | ━ | [376 empty] | 三心拱巷道 净宽: 4; 三心拱巷道 净高: 4; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.3 | 采区变电所 | 锚网喷砼 | 100 | 14.33 | 15.34 | 96 | 1472.64 | 97 |  | 245 | 1.536 |  |  | 4.5m×3.5m，6个 | 800 | 225 | 243 | 1.8 | [224 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [357 empty] | 三心拱巷道 净宽: 4.5; 三心拱巷道 净高: 3.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.4 | 上部水泵房 | 锚网喷砼 | 150 | 28.24 | 30.57 | 30 | 917.1 | 70 |  | 80 | 0.48 |  |  | 5.0m×6.0m | 800 | 244 | 255 | 1.1 | [243 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [345 empty] | 三心拱巷道 净宽: 5; 三心拱巷道 净高: 6; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.5 | 上部水仓 | 锚网喷砼 | 100 | 23.24 | 24.59 | 120 | 2950.8 | 162 |  | 305 | 1.92 |  |  | 5.0m×5.0m | 120 | 256 | 266 | 1 | [255 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [334 empty] | 三心拱巷道 净宽: 5; 三心拱巷道 净高: 5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.6 | 爆破器材库回风联巷 | 喷砼 | 100 | 5.81 | 6.49 | 36 | 233.64 | 24 | [5 empty] | 2.5m×2.5m | 120 | 267 | 270 | 0.3 | [266 empty] | ━ | ━ | ━ | ━ | [330 empty] | 三心拱巷道 净宽: 2.5; 三心拱巷道 净高: 2.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.7 | 爆破器材库运输巷 | 砼，C25 | 200 | 5.81 | 7.2 | 60 | 432 | 83 | [5 empty] | 2.5m×2.5m | 120 | 271 | 276 | 0.5 | [270 empty] | ━ | ━ | ━ | ━ | ━ | ━ | [324 empty] | 三心拱巷道 净宽: 2.5; 三心拱巷道 净高: 2.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.8 | 爆破器材库 | 砼，C25 | 200 | 5.81 | 7.2 | 60 | 432 | 83 | [5 empty] | 2.5m×2.5m | 800 | 277 | 282 | 0.5 | [276 empty] | ━ | ━ | ━ | ━ | ━ | ━ | [318 empty] | 三心拱巷道 净宽: 2.5; 三心拱巷道 净高: 2.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.9 | 爆破器材库专用回风天井 | 喷砼 | 100 | 4.91 | 5.7226 | 150 | 858.3975 | 122 | [5 empty] | φ2.5m | 80 | 283 | 302 | 1.9 | [282 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [298 empty] | 圆形巷道 净直径: 2.5; 圆形巷道 掘直径: 2.7; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.10 | 井下避难仓硐室 | 锚网 |  | 14.87 | 14.87 | 30 | 446.1 | 0 |  | 80 | 0.48 |  |  | 4.0m×4.0m | 800 | 215 | 221 | 0.6 | [214 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [379 empty] | 三心拱巷道 净宽: 4; 三心拱巷道 净高: 4; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.11 | 无轨设备维修硐室 | 砼，C30 | 300 | 66.3 | 73.03 | 50 | 3651.5 | 337 | [5 empty] | 9.0m×8.0m | 800 | 222 | 268 | 4.6 | [221 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [332 empty] | 三心拱巷道 净宽: 9; 三心拱巷道 净高: 8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.12 | 无轨设备维修硐室仓库 | 锚网喷砼 | 100 | 11.37 | 12.38 | 4.5 | 55.71 | 5 |  | 17 | 0.072 |  |  | 3.0m×4.0m | 800 | 269 | 270 | 0.1 | [268 empty] | ━ | ━ | [330 empty] | 三心拱巷道 净宽: 3; 三心拱巷道 净高: 4; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.13 | 无轨设备维修硐室控制室 | 锚网喷砼 | 100 | 11.39 | 12.34 | 6 | 74.04 | 6 |  | 20 | 0.096 |  |  | 3.5m×3.5m | 800 | 271 | 272 | 0.1 | [270 empty] | ━ | ━ | [328 empty] | 三心拱巷道 净宽: 3.5; 三心拱巷道 净高: 3.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.14 | 井下无轨设备硐室联络道 | 锚网 | 100 | 14.87 | 15.95 | 20 | 319 | 22 |  | 55 | 0.32 |  |  | 4.0m×4.0m | 120 | 273 | 275 | 0.2 | [272 empty] | ━ | ━ | ━ | [325 empty] | 三心拱巷道 净宽: 4; 三心拱巷道 净高: 4; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.15 | 电机车维修硐室1 | 砼，C30 | 300 | 66.3 | 73.03 | 50 | 3651.5 | 337 | [5 empty] | 9.0m×8.0m，2个 | 800 | 276 | 322 | 4.6 | [275 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [278 empty] | 三心拱巷道 净宽: 9; 三心拱巷道 净高: 8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
12.16 | 电机车维修硐室2 | 砼，C30 | 300 | 66.3 | 73.03 | 50 | 3651.5 | 337 | [5 empty] | 9.0m×8.0m，2个 | 800 | 276 | 322 | 4.6 | [275 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [278 empty] | 三心拱巷道 净宽: 9; 三心拱巷道 净高: 8; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 829.5 | 20154.9075 | 1712 | 0 | 875 | 5.336 | 0 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13 | 充填+泄水 | [15 empty] | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13.1 | 充填平巷 | 锚网 | 0 | 5.81 | 5.81 | 200 | 1162 |  |  | 505 |  |  |  | 2.5m×2.5m |  |  | 0 | 0 | [600 empty] | 三心拱巷道 净宽: 2.5; 三心拱巷道 净高: 2.5; 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13.2 | 充填钻孔 |  |  | 0 | 0.126 | 500 | 63 | [6 empty] | 二采区660～410m，2个 |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13.3 | 泄水钻孔 |  |  | 0 | 0.126 | 300 | 37.8 | [6 empty] | 一采区210～60m，2个 |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 |  |  |  |  | 1000 | 1262.8 | 0 | 0 | 505 | 0 | 0 | 0 |  |  |  | 0 | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13 | 采准工程 | [16 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13.1 | 采准工程1 | [5 empty] | 25500 | [7 empty] | 1000 | 23 | 278 | 25.5 | [22 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [322 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13.2 | 切割工程1 | [5 empty] | 8050 | [7 empty] | 1000 | 279 | 360 | 8.1 | [278 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [240 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13.3 | 采准工程2 | [5 empty] | 10770 | [7 empty] | 1000 | 96 | 204 | 10.8 | [95 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [396 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
13.4 | 切割工程2 | [5 empty] | 9835 | [7 empty] | 1000 | 205 | 303 | 9.8 | [204 empty] | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | ━ | [297 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 小计 | [5 empty] | 54155 | [10 empty] | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 二采区合计 |  |  |  |  | 31284.5 | 602829.4875 | 39347 | 0 | 1380 | 5.336 | 3 | 324 |  |  |  |  | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
| 总计 |  |  |  |  | 31284.5 | 602829.4875 | 39347 | 0 | 1380 | 5.336 | 3 | 324 |  |  |  |  | 0 | [600 empty] | 圆形巷道 掘直径: 0; 矩形巷道 掘面积: 0; 梯形巷道 掘面积: 0
Note on J2: 王雪旺: 1、一般主要斜坡道或运输巷道会产生铺底矿石。 2、轨道运输会增加铺底厚，只是计算巷道高，，但不一定铺碎石。 3、铺底碎石自行计算，铺底厚*净宽*长度。
Note on N1: 王雪旺: 1、全装备按0.5t/m估算。 2、仅装梯子间按0.1t/m估算。

## 使用说明
使用说明：
1、不可插入行，不可插入行，不可插入行。可复制一行，并插入复制的单元格，否则，进度计划条无法显示。
2、本表为某项目基建工程量表+基建进度计划表。仅供参考，不作评论。
3、WW-XH列，为计算列，可将巷道规格输入，巷道断面计算结果自动在E列和F列显现。
4、若在WW列填写了铺底厚，而J列未填写铺底碎石体积，则铺底自动按支护量计算。
5、Q列和R列的开始时间和结束时间：开始时间需等于上一项的结束时间+1。结束时间自动生成。
6、P列输入施工定额后，S列完成时间自动生成。
7、出表的时候，不需要的行列可以整行或整列的隐藏。